## Slide 1: Drug designer database
Carlos Dominguez(Developer, Tester, scrum master, everything…) Product Owner: Dr. Luis Arroyo

## Slide 2: Presentation
What’s my project about?

## Slide 3: Stories in spring 3
43 ---- = 1.08 points per hour 40
User Story | Estimated | Current | 
#201 email defect | 4 | 4 | 
#202 pictures name defect | 4 | 5 | 
#203 import defect | 16 | 14 | 
#204 update about us page | 4 | 3 | 
#205 change look of the system | 16 | 17 | 
 | 44 | 43 | Total
Total Speed =

## Slide 4: Mingle Daily Scrum
Daily Scrum # | Date | Action | 
237 | 23/3/2015 | Pictures Defect | 4hrs
238 | 24/3/2015 | Pictures Defect Import Defect | 1 hr 3 hrs
239 | 25/3/2015 | Import Defect | 4 hrs
240 | 26/3/2015 | Import Defect | 4 hrs
241 | 27/3/2015 | Import Defect Change look of the system Meet with client | 1 hrs 5 hrs 1 hr
242 | 30/3/2015 | Change look of the system | 4 hrs
243 | 31/3/2015 | Change look of the system | 4 hrs
244 | 01/4/2015 | Change look of the system | 4 hrs
245 | 02/4/2015 | Update about us page | 4 hrs
246 | 03/4/2015 | Pictures name defect Meet with client | 5 hrs 2 hrs

## Slide 5: Change look of the System User Story

## Slide 6: This is how it looked before

## Slide 7: This is how it looks now

## Slide 8: Invite Email Defect User Story

## Slide 9: Invite email Use Case
Name: 175_createUser
Participating actor: admin user
Entry condition: User is logged in the system User is in the User Management page. User has admin rights
Exit condition: User invite is sent
Event flow: User enter the email of the user to be invited User clicks the invite button. System confirms that the invitation has been sent.

## Slide 10: Invite new user sequence Diagram

## Slide 11: Class diagram

## Slide 12: DEMO

## Slide 13: Documents updated
Feasibility Study
Required Documents
Design Document

## Slide 14: Use Case Diagram

## Slide 15: BurnUP Chart

## Slide 16: Current Sprint
User Story | Estimated | Accepted
#201 import defect | 4 | 4
#202 add compound defect | 4 | 4
#203 compound info defect | 16 | 16
#204 edit compound defect | 8 | 8
 | 32 | 32

## Slide 17: Retrospective